## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | new members join the group | 1 | 2 | 2 | 2*1*2=4 | all members | 2022-10-20 | Any additional role(s) that a current member is taking on will be handed over to new members to allow more even distribution of work | no new members so far | Open
| Lack of motivation or responsibility | members are not able to meet deadlines | 2 | 4 | 4 | 32 | all members | 2022-10-20 | work will be distributed evenly amongst members and expectations are clear from the start. Weekly meetings will be set up in order to track each member's progress and status | all members have attended meetings and kept up with work so far | Open
| Conflict on speciality | members may have conflict in their speciality | 2 | 1 | 2 | 4 | all members | 2022-10-20 | Talk about the speciality before assigning each roles to every team members | all members are not having any conflict | Open
Communication | duplicate work | multiple members work on the same issue and have conflicting code | 4 | 4 | 4 | 64 | all | 2022-10-20 | Tasks will be clearly assigned weekly to ensure that each member is aware of what others are doing in order to avoid overlapping work | No conflicting tasks so far | Open
Technology competence | Not familiar with the framework used | members are not experienced in the framework (Android Studio) | 1 | 1 | 1 | 1 | all | 2022-09-12 | All members have experience working with Android studio | All members have experience working with Android studio | Closed
| Not familiar with the programming language used | members are not experienced in the programming language (Java) | 1 | 1 | 1 | 1 | all | 2022-09-12 | All members have experience programming in Java | All members have experience programming in Java | Closed
Testing | Not familiar with unit testing | members do not have QA testing experience | 2 | 2 | 2 | 8 | all | 2022-09-12 | All members will have a part in unit testing to ensure that testing is complete and sufficient | All members have some sort of working knowledge on testing practices and are willing to do outside research for anything that is lacking | Closed
Design and implementation | Messy code | members write unreadable and unorganized code | 2 | 3 | 2 | 12 | all | 2022-10-20 | All members will have work checked over and use best practices in coding, while also providing sufficient documentation | All members are aware of best programming practices | Open
| Complex design | simplistic design goal is not met | 3 | 4 | 3 | 36 | all | 2022-10-20 | All members will check over each other's work and provide feedback during weekly meetings | All members understand that this project is aimed at elderly members of the population with minimal technical experience/knowledge | Open
Integration and deployment | Not enough time for integration and deployment | deadlines are not met and integration and deployment is not ready at the end of each iteration | 3 | 4 | 3 | 36 | all | 2022-10-20 | A project plan will be determined in iteration 1 to set up deadlines and configure timelines | All members will complete thier work on time | Open