## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/5 - 9/12 | Team met for the first time and discussed project ideas, roles, and risks | n/a | n/a | MedTracker application targeted towards the elderly population to help keep track of medications | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1 | 9/13 - 9/27 | -Team met 2 times within the two week period -Team created and assigned user stories -Team created GUI and database components | Difficulty working with fragments in navigation bar | Slower task completion than expected | UI creation Database creation Component creation Unit test framework introduction Unit tests | 7 | 2 | 2 | 3 | 2 | 20 |  | 2
2 | 9/27 - 10/10 | - Team met 2 times with the two week period - Team scaled back the scope of the project - Team decided on a new architecture - Team refactored some GUI components - Team integrated some functionality on top of front end | Complexity of DAO slowing team down | Scope is still rather large as some technologies are new to team | - Finish integration - Fully transition to MVVM - Unit test database code | 5 | 9 | 4 | 3 | 3 | 15 |  | 2
3 | 10/10 - 10/18 | - Team met 3 times during the final week - Fully integrations of features - Hooked up backend to front end - Created notifications - Added edit functionality to medications - Updated UI - Transitioned archeticture to MVVM |  |  | Submit final | 12 | 0 | 8 | 8 | 0 | 22 |  | 6

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Andrew Gieraltowski |  | Week of 9/13 - 9/29 Added requirements for two stories that were accepted into the project Week 9/29 - 10/10 Updated pivotal tracker with status Created and assigned new tasks based on feedback from standup |  | 9/24 Filled out STD 10/10 Updated STD |  | Week of 9/13 - 9/29 Created Project, Pushed it to github, Created two modules (Medicine, Schedule) Week of 9/29 - 10/10 Integrated event handler for adding medication Updated surrounding modules | Week of 9/13 - 9/29 Chose and introduce Junit Created Unit tests for two modules Week of 9/29 - 10/10 Manual testing of all features Manual testing of new features |  | Week of 9/13-9/29 Active on discord Gathering status Week of 9/29 - 10/10 Task delegation Weekly standups Status gathering

## Yuan Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and implementation leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5-9/12 | 10.5 | 9.5 | 1 | 0 - learn git and Android studio 1 - define basic level of requirements for the project 5 - make project plan, create pivotal tracker account 6 - set up git and Android studio 7 - research similar products and their user interfaces | 3 | 1 |  |  |  | 0.5 | 2 | 3 | 1. Write 3 functional requirements 2. Set up git on Github Desktop 3. Install Android Studio | 1. Not using Android Studio for a while 2. Not familiar with pivotal tracker | 1. Search on Stack Overflow and related Youtube videos 2. Listen to lecture recordings with setting up pivotal tracker | 1. Create basic UI for the project 2. Create connections for different interfaces | 8
| 9/13-9/27 | 14 | 13 | 1 | 0 - learn Android studio functionalities 1 - define some high level requirements 2 - design user interfaces for the project 4 - run the interfaces on a virtual android phone 5 - share with team members about the coding issues | 3 | 1 | 7 |  | 1 | 1 |  |  | 1. Design 3 user interfaces 2. Elaborating on the interfaces to be more user-friendly 3. Create user stories on Pivotal Tracker 4. Create connections between interfaces | 1. Android Studio unable to start the virtual phone 2. Trouble creating navigation bar | 1. Search website for alternative visualization plan 2. Use alternative bars to replace navigation bar | 1. Generate more user interfaces 2. Create connections among more interfaces 3. Relate the UI to the database | 12
| 9/28-10/10 | 18 | 17 | 1 | 0 - learn Android studio functionalities 1 - delete some functional requirements and focuses on specific ones 2 - prettify the add medication UI and the home UI 3 - implement the room database and make correlations with the UI 5 - test the app on Android studio virtual phone | 4 | 1 | 8 | 2 |  | 2 |  |  | 1. Prettify 2 user interfaces 2. Generate connection between UI and the database 3. Implementing date and time picker view to the APP 4. Write error handling fucntions | 1. Trouble understanding database language 2. Trouble make connections between the database and the UI | 1. Ask team members who are in charge of the database design for help 2. Search on the website for similar answers | 1. Adding the medication history functionality 2. Allow users to edit their medication info | 9
| 10/11-10/18 | 21 | 20 | 1 | 0 - learn Android studio functionalities 1 - add the edit medication functionality 2 - add the edit button and the delete button for the cardview 3 - implement startactivityforresult feature on Android Studio 4 - run the app on Android studio virtual phone 5 - share with team members about the code | 4 | 10 | 1 | 3 | 1 | 1 |  |  | 1. Create the edit medication button 2. Create the functionality for user to edit existing medication 3. Make interaction between edit and the database | 1. Trouble understanding database language | 1. Ask Divya(in charge of database design) for help |  | 10

## Andrew Gieraltowski
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/12 | 3 | 2 | 1 | 0 - Learn requirements for class 1 - Define requirements needed for app development 5 - Define project, define team roles 6 - Initialize repo, make sure team can push/pull | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0 | 1. Set up github repo 2. Set up google drive 3. Download files and push them to github 4. Participate in meetings/project planning |  | 1. Continue research and development of application | 2 - Research 3 - Project environment setup 2 - Communication/Documentation | 8
2022-02-03 | 9/13 - 9/27 |  |  |  | 0 - Learn Junit and unit tests for java/android 1 - Create tasks in Pivotal Tracker 2 - Design modules for use in the application 3 - Implement the modules 4 - Create unit tests for the modules 5 - Communicated completion of modules and documentation to the team 6 - Maintain github repository for the team | 0.5 | 1 | 1 | 2 | 2 | 0.5 | 1 |  | 1. Modules and unit tests 2. Ran standup 3. Managed github repo 4. Created tickets and assigned them 5. Manage documentation (filled out STD) |  | 1. Finish iteration 1 code 2. Gather documentation and push to github 3. Create release |  | 7.5
2022-04-05 | 9/28-10/11 |  |  |  | 0 - Familiarize myself with MVVM architecture and LogCat debugging methods 1 - Maintain pivotal tracker tasks for myself and team 2 - Integrate on click event handling for adding medication 3 - Make neccessary changes/Create pull request 4 - Ran functional tests and verified with LogCat 5 - Delegated tasks to team members, ran meetings, asked for status 6 - Maintain github repo for team | 1 | 0.5 | 4 | 3 | 1 | 1 | 1 |  | 1. PR for on click event integration 2. Ran standup 3. Github repo management 4. Task delegation 5. Updated STD |  | 1. Finish iteration 2 code 2. Swap to MVVM architecture 3. Gather documentation and push to github 4. Create release | 4 - Itegration 3 - Testing 4 - Additional Features 2 - Documentation | 13
6 | 10/12-10/18 |  |  |  | 3 - Integrated the core functionality, connecting the backend and front end 3 - Created notification feature, tested and documented 4 - Manual testing of all integrated components 5 - Made PR's asked for review, communicated progress to team 6 - Pushed changes to github | 0 | 0 | 0 | 6 | 2 | 0.5 | 0.5 |  | 1. PR for integrated components 2. Documentation update 3. Team coordingation 4. Github repo management 5. Presentation |  | 1. Wrap up project 2. Update documentation 3. Help create final presentation |  | 9

## Divya Thomas
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5-9/12 | 2 | 2 | 2 | 0 - learn/research other android apps or any features that can be included in the project 5 - met with team to discuss project proposal and set up roles and expectations | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1. Complete documents required for iteration 0 2. Set up git, commit a test message on git (Lab1) 3. Research possible features and design for the application 4. Record iteration 0 presentation | 1. Not very familar with what is expected from us in each iteration. A clear guideline would be appreciated from instructors. 2. Not clear on timelines and goals for each iteration | 1. Set up a meeting or discuss on chat a tentative timeline of project completion and task distributions | 2 - set up a basic design/wireframe of project and features to include 3 - distribute tasks to members 5 - put together a tentative timeline for deadlines | 6
2 | 9/12-9/26 | 13 | 11 | 2 | 0 - learn java implementation techniques for room database in Andriod studio 2 - design database structure for medication and accounts tables 3 - implement Room database in application 4 - configure unit tests for database class (still in progress) 5 - filled out SDD | 2 | 0 | 1 | 5 | 2 | 1 | 0 | 0 | 1. Completed database configuration 2. Started setting up database unit tests (still in progress due to some junit configuration issues) 3. Helped complete SDD | 1. Encountered issues in junit testing regarding detecting test cases 2. Conflicting references between DB and UI will require some restructuring when connecting the functionalities of the two together | 1. Further investigate and discuss jUnit testing issues with team and professor to debug and resolve. 2. Reconfigure either db implementation or UI implementation to sync | 3 - connect db to UI implementation (add Medication/ Patient features especially) 4 - successfully configure unit testing on all database classes 5 - meet with team and discuss intentions with the UI and DB structure | 10
3 | 9/27-10/11 | 15 | 13 | 2 | 1 - reassess database code to minimize scope 2 - worked towards implementing design patterns and new architecture 3 - implemented strategy pattern and began restructure into MVVM design 4 - continued work on database test implementations (still struggling with this) | 0 | 2 | 2 | 7 | 2 | 0 | 0 | 0 | 1. Restructured database design to become more localized 2. Implemented a strategy pattern and refactored Schedule class in order use this pattern to automatically update take times | 1. Encountered issues in junit testing regarding detecting test cases 2. Conflicting references between DB and UI will require some restructuring when connecting the functionalities of the two together | 1. Will research and find examples of database testing 2. Will primarily focus on configuration and communication between UI and database | 3 - finish UI and database configuration/communication 4 - complete and finalize all testing and configurations 5 - complete and finalize all documentation | 20
4 | 10/11 - 10/18 | 17 | 14 | 3 | 2- Set up MVVM architecture and integrated with the application 3- Finished UI integration with database to ensure persistent data 5 - Finalized and completed documentation, final presentation | 0 | 0 | 8 | 4 | 0 | 2 | 0 | 0 | 1. Created 2 Viewmodels and a singleton database 2. Integrated Database with application code 3. Set up refresh functionality on any medication edit, add, or delete | 1. Junit Testing configuration of the database class continued to fail after many attempts at restoration | 1. Finish documentation updates 2. Complete final presentation 3. Submit project | N/A | 0

## Haiyang Lu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/13 | 3 | 2 | 2 | 0 - learn the git and android developing tutorials 5 - Met with other teammates, assign team roles 6 - Pull and push git files to test if the repository works | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1. Set up and test the git repository 2. Complet two sections for the SPPP files 3. Participate in group meeting |  |  | 1. Set up enviroment for the project 2. Unified development and test environment 3. Group discussion about product's development process | 7
2022-02-03 | 9/13 - 9/27 |  |  |  | 0 - Learn how to access alarm and sound system on Android 1 - Create tasks in Pivotal Tracker 2 - Make Iteration presentation 5 - Meet with team members and discuss tasks | 2 | 1 | 4 | 0 | 0 | 2 | 0 | 0 | 1. Research for Android alarm and sound system implementation 2. Tasks created on pivotal tracker 3. Make the slides and presentation for iteration 1 4. Participate in group meeting |  |  | 1. Create UI page for care takers 2. Switch Account function between patients and care takers 3. Continue research on alarm and sound system implementation | 7
2022-04-05 | 9/28-10/11 | 10.5 | 8.5 | 2 | 0 - Learn the method for UI and activity testing 1 - Follow up with pivotal tracker tasks for the team 2 - Create the activity test for the main page 4 - Configure test for home UI 6 - Update new version for activity test 7 - Update activity test case for STD file | 2 | 0.5 | 4 | 0 | 1 | 0 | 1 |  | 1.Create activity test for main page 2. Set up test environment for UI 3. Testing the home UI 4. Update STD file | 1. Having trouble while testing different function within the home interface 2. Execution failed for task 'connectedDebugAndroidTest' | 1. Watch online turtorial for help 2. Complete all activity and UI tests for every interface | 1.Integrate the UI and the database 2. Configure all the possible activity test for UI 3. Follow up with all the documentations and presentation | 11
6 | 10/12 - 10/18 | 8 | 6 | 2 | 0- Learn how to set up notification in adroid device 1- Follow up with the pivotal tracker tasks 4 - Configure test for activity 5 - Meet up with team for the final presentation 7 - Complete documentations for final interation | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 2 | 1. Contintue with the UI test 2. Reseach for notification function implemetation 3. Documentation for final iteration 4. Presentation for iteration 3 |  |  |  | 6