## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/5 - 9/12 | Team met for the first time and discussed project ideas, roles, and risks | n/a | n/a | MedTracker application targeted towards the elderly population to help keep track of medications | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1 | 9/13 - 9/27 | -Team met 2 times within the two week period -Team created and assigned user stories -Team created GUI and database components | Difficulty working with fragments in navigation bar | Slower task completion than expected | UI creation Database creation Component creation Unit test framework introduction Unit tests | 7 | 2 | 2 | 3 | 2 | 20 |  | 2
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Andrew Gieraltowski |  | Week of 9/13 - 9/29 Added requirements for two stories that were accepted into the project |  | 9/24 Filled out STD |  | Week of 9/13 - 9/29 Created Project, Pushed it to github, Created two modules (Medicine, Schedule) | Week of 9/13 - 9/29 Chose and introduce Junit Created Unit tests for two modules |  | Week of 9/13-9/29 Active on discord Gathering status

## Yuan Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and implementation leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5-9/12 | 10.5 | 9.5 | 1 | 0 - learn git and Android studio 1 - define basic level of requirements for the project 5 - make project plan, create pivotal tracker account 6 - set up git and Android studio 7 - research similar products and their user interfaces | 3 | 1 |  |  |  | 0.5 | 2 | 3 | 1. Write 3 functional requirements 2. Set up git on Github Desktop 3. Install Android Studio | 1. Not using Android Studio for a while 2. Not familiar with pivotal tracker | 1. Search on Stack Overflow and related Youtube videos 2. Listen to lecture recordings with setting up pivotal tracker | 1. Create basic UI for the project 2. Create connections for different interfaces | 8
| 9/13-9/27 | 14 | 13 | 1 | 0 - learn Android studio functionalities 1 - define some high level requirements 2 - design user interfaces for the project 4 - run the interfaces on a virtual android phone 5 - share with team members about the coding issues | 3 | 1 | 7 |  | 1 | 1 |  |  | 1. Design 3 user interfaces 2. Elaborating on the interfaces to be more user-friendly 3. Create user stories on Pivotal Tracker 4. Create connections between interfaces | 1. Android Studio unable to start the virtual phone 2. Trouble creating navigation bar | 1. Search website for alternative visualization plan 2. Use alternative bars to replace navigation bar | 1. Generate more user interfaces 2. Create connections among more interfaces 3. Relate the UI to the database | 12

## Andrew Gieraltowski
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/12 | 3 | 2 | 1 | 0 - Learn requirements for class 1 - Define requirements needed for app development 5 - Define project, define team roles 6 - Initialize repo, make sure team can push/pull | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0 | 1. Set up github repo 2. Set up google drive 3. Download files and push them to github 4. Participate in meetings/project planning |  | 1. Continue research and development of application | 2 - Research 3 - Project environment setup 2 - Communication/Documentation | 8
2022-02-03 | 9/13 - 9/27 |  |  |  | 0 - Learn Junit and unit tests for java/android 1 - Create tasks in Pivotal Tracker 2 - Design modules for use in the application 3 - Implement the modules 4 - Create unit tests for the modules 5 - Communicated completion of modules and documentation to the team 6 - Maintain github repository for the team | 0.5 | 1 | 1 | 2 | 2 | 0.5 | 1 |  | 1. Modules and unit tests 2. Ran standup 3. Managed github repo 4. Created tickets and assigned them 5. Manage documentation (filled out STD) |  | 1. Finish iteration 1 code 2. Gather documentation and push to github 3. Create release

## Divya Thomas
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5-9/12 | 2 | 2 | 2 | 0 - learn/research other android apps or any features that can be included in the project 5 - met with team to discuss project proposal and set up roles and expectations | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1. Complete documents required for iteration 0 2. Set up git, commit a test message on git (Lab1) 3. Research possible features and design for the application 4. Record iteration 0 presentation | 1. Not very familar with what is expected from us in each iteration. A clear guideline would be appreciated from instructors. 2. Not clear on timelines and goals for each iteration | 1. Set up a meeting or discuss on chat a tentative timeline of project completion and task distributions | 2 - set up a basic design/wireframe of project and features to include 3 - distribute tasks to members 5 - put together a tentative timeline for deadlines | 6
2 | 9/12-9/26 | 13 | 11 | 2 | 0 - learn java implementation techniques for room database in Andriod studio 2 - design database structure for medication and accounts tables 3 - implement Room database in application 4 - configure unit tests for database class (still in progress) 5 - filled out SDD | 2 | 0 | 1 | 5 | 2 | 1 | 0 | 0 | 1. Completed database configuration 2. Started setting up database unit tests (still in progress due to some junit configuration issues) 3. Helped complete SDD | 1. Encountered issues in junit testing regarding detecting test cases 2. Conflicting references between DB and UI will require some restructuring when connecting the functionalities of the two together | 1. Further investigate and discuss jUnit testing issues with team and professor to debug and resolve. 2. Reconfigure either db implementation or UI implementation to sync | 3 - connect db to UI implementation (add Medication/ Patient features especially) 4 - successfully configure unit testing on all database classes 5 - meet with team and discuss intentions with the UI and DB structure | 10

## Haiyang Lu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/13 | 3 | 2 | 2 | 0 - learn the git and android developing tutorials 5 - Met with other teammates, assign team roles 6 - Pull and push git files to test if the repository works | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1. Set up and test the git repository 2. Complet two sections for the SPPP files 3. Participate in group meeting |  |  | 1. Set up enviroment for the project 2. Unified development and test environment 3. Group discussion about product's development process | 7
2022-02-03 | 9/13 - 9/27 |  |  |  | 0 - Learn how to access alarm and sound system on Android 1 - Create tasks in Pivotal Tracker 2 - Make Iteration presentation 5 - Meet with team members and discuss tasks | 2 | 1 | 4 | 0 | 0 | 2 | 0 | 0 | 1. Research for Android alarm and sound system implementation 2. Tasks created on pivotal tracker 3. Make the slides and presentation for iteration 1 4. Participate in group meeting |  |  | 1. Create UI page for care takers 2. Switch Account function between patients and care takers 3. Continue research on alarm and sound system implementation | 7